## Sheet1
Binfire Project Plan Template for Internal Solutions Development
Task No | Task | Scheduled Start Date | Scheduled End Date | Dependencies | Estimated Effort (Days) | Resource A | Resource B | Resource C | Resource D | Resource E | Resource F | Comments
1 | Develop Solution Plan
1.1 | Develop Project Plan
1.1.1 | Define Project Scope and Objectives
1.1.2 | Select Executive Sponsor
1.1.3 | Secure Project Resources including Team
1.2 | Develop Communications Plan
1.2.1 | Establish Steering Committee
1.2.2 | Draft Communications Plan
1.2.3 | Solicit Feedback from Key Stakeholders
1.2.4 | Finalize Communications Plan
1.3 | Develop Risk Mitigation Plan
1.3.1 | Identify Potential Risks and Issues
1.3.2 | Develop Risk Mitigation Plan
1.4 | Project Kick Off
2 | Develop Solutions Specifications
2.1 | Conduct Solutions Workshops with Representatives from Impacted Groups
2.2 | Interview Key Stakeholders (including Partners and Customers)
2.2.1 | Conduct In-Person Interviews
2.2.2 | Augment Interviews with Surveys
2.2.3 | Write Up and Validate with Follow Ups
2.2.4 | Summarize and Document
2.3 | Research Previous Initiatives
2.4 | Map Current State and Existing Processes
2.5 | Review Benchmark Research
2.6 | Conduct Root Cause Analysis
2.7 | Define High Level Requirements and Gaps
2.8 | Prioritize Requirements based on Stakeholder Feedback
2.9 | Develop Solutions Requirements Report
3 | Solutions Design
3.1 | Conduct Solutions Design Workshop
3.2 | Identify and Secure Resources for Implementation Team
3.3 | First Pass Solutions Design
3.3.1 | Conduct Impact Assessment
3.3.2 | Determine Costs and Benefits
3.3.3 | Define Metrics and KPI's
3.3.4 | Gain Agreement on Prioritization of Solution Functionalities
3.4 | Create Solutions Design Report
4 | Develop Implementation Plan
4.1 | Solicit Feedback from Key Stakeholders
4.2 | Draft Implementation Plan
4.3 | Finalize Implementation Plan
4.4 | Present Plan to Key Stakeholders
5 | Implementation (Execution)
Based on Implementation Plan
6 | Evaluation
6.1 | Prepare Reports based on Metrics and KPI's
6.2 | Write Management Report