## Sheet1
Binfire Project Plan Template for Online Advertising Campaign
Task No | Task | Scheduled Start Date | Scheduled End Date | Dependencies | Estimated Effort (Days) | Project Sponsor | Project Manager | Creative Director | PPC Manager | SEO Manager | Social Media Manager | Writer | Design | Agency | Other | Comments
1 | Determine Campaign Objectives
1.1 | Determine Campaign Goals
1.1.1 | Define Goals based on SMART (Specific, Measurable, Attainable, Realistic and Time Bound)
1.1.2 | Review Competitor Campaigns
1.1.3 | Analyze Data from Social and Google Analytics
1.2 | Determine Overall Budget
1.3 | Obtain Management Approval for Budget
2 | Define Customer Persona and Channel Mix
2.1 | Select Part of the Marketing Funnel for Focus
2.2 | Identify Target Demographic and Psychographic
2.3 | Finalize the Selection of Customer Persona
2.3.1 | Use tools such as Twitter Analytics, Pinterest Analytics, Facebook Insights and Tweriod to understand Customer Persona
2.4 | Determine which Channel is Relevant for Customer Persona
3 | Select Campaign Resources
3.1 | Select Team for Creative, Analytics, Distribution etc.
3.2 | Select External Vendors/Agencies
3.3 | Draft Campaign Execution Plan
3.4 | Sign off on Execution Plan by Key Stakeholders
4 | Campaign Design
4.1 | Develop Campaign Graphics that is Consistent with Branding
4.2 | Develop Content
4.3 | Create Call-To-Actions that are Consistent with Campaign Goals
4.4 | Create Campaign Schedule
4.5 | Meet and Brief with Company Attendees
5 | Campaign Analytics
5.1 | Monitor Lead Tracking
5.2 | Record Lessons Learned for Future Campaigns