## Sheet1
Binfire Project Plan Template for Software Development Project
Task No | Task | Scheduled Start Date | Scheduled End Date | Dependencies | Estimated Effort (Days) | Project Sponsor | Project Manager | Business Analyst | Development SME | Deployment SME | Operations | Support | Testing | Vendor | Training | Comments
1 | Project Initiation
1.1 | Define Project Charter and Goals
1.1.1 | Define Project Scope
1.1.2 | Define High Level Requirements
1.1.3 | Select Initial Project Roles
1.1.4 | Estimate High-Level Budget
1.1.5 | Finalize Charter and Gain Management Sign-Off
1.2 | Business Case Development
1.2.1 | Define Criteria for Project Success
1.2.2 | Develop Detailed Business Plan
1.2.3 | Executive Sign-Off
2 | Plan Project
2.1 | Develop Project Work Plan
2.1.1 | Develop Budget
2.1.2 | Develop Schedule
2.1.3 | Develop Resource Plan
2.1.4 | Develop Communication Plan
2.1.5 | Develop Metrics & Measurement Plan
2.1.6 | Finalize Plan and Gain Management Sign-Off
3 | Design
3.1 | High-Level Design (including Prototypes, Mock-ups and Diagrams)
3.2 | Proof of Concept
3.3 | Detailed Design
3.4 | Technical Specification
3.5 | Design Completion Sign-Off
4 | Development
4.1 | Purchase of Hardware and Software
4.2 | Development of Application Based on Technical Specifications
4.3 | Development Completion Sign-Off
5 | Installation
6 | Testing and Documentation
6.1 | Develop Testing Plan
6.1.1 | Define Testing Types and Criteria
6.1.2 | Develop Testing Scenarios
6.1.3 | Sign-Off on Testing Scenarios
6.2 | Conduct Testing
6.2.1 | Perform System Test
6.2.2 | Perform Function Test
6.2.3 | Perform Unit Test
6.2.4 | Perform Test on Integration
6.2.5 | Quality Assurance Testing
6.3 | Documentation
6.3.1 | Document Testing Results
6.3.2 | Recommendations for Modifications based on Results
7 | Training
7.1 | Develop Training Plan
7.1.1 | Select Training Methodology (Instructor Led or e-Learning)
7.1.2 | Develop IT Support Training Plan
7.1.3 | Develop End User Training Plan
7.1.4 | Develop Administration User Training Plan
7.1.5 | Develop Metrics for Evaluation
7.2 | Training Readiness
7.2.1 | Identify Training Resources
7.2.2 | Conduct Train-the-Trainer (TTT) Sessions
7.2.3 | Create Schedule
7.3 | Training Execution
8 | Project Close and Analysis
8.1 | Benefits Utilization Assessment based on Project Goals
8.1.1 | Goal A
8.1.2 | Goal B
8.1.3 | Goal C
8.2 | Conduct Postmortem Analysis
8.2.1 | Compare Actual Budget versus Estimate
8.2.2 | Team Member Feedback
8.2.3 | Stakeholder Feedback
8.2.4 | Partner Feedback
8.2.5 | Create Project Close Report