## Sheet1
Binfire Project Plan Template for Trade Show
Task No | Task | Scheduled Start Date | Scheduled End Date | Dependencies | Estimated Effort (Days) | Project Sponsor | Project Manager | Procurement | Marketing SME | Logistics | Support | Agency | Vendor | Comments
1 | Book Venue
1.1 | Define High Level Objectives
1.2 | Select Specific Trade Show based on Objectives
1.3 | Select Booth Location
1.4 | Determine Overall Budget
1.5 | Review Contract
1.6 | Submit Application and Initial Payment
2 | Develop Trade Show Plan
2.1 | Define Specific Trade Show Goals and Success Factors
2.2 | Identify Short List of Vendors
2.2.1 | Marketing, Design and Signage
2.2.2 | Exhibit Hall Logistics
2.2.3 | Catering
2.2.4 | Travel
2.2.5 | Giveaways
2.2.6 | Printing and Other Materials
2.2.7 | Solutions for Lead Tracking
2.3 | Finalize Plan and Gain Management Sign-Off
3 | Pre-Event Activities
3.1 | Finalize Selection of Vendors
3.2 | Sign all Vendor Related Contracts
3.3 | Book Travel and Accommodations
3.4 | Develop Floor Plan for Exhibit
3.5 | Book Additional Meeting Rooms
3.6 | Identify List of Attendees and Secure Attendance Commitment
3.7 | Communicate Plan to all Attendees
4 | Onsite Logistics Activities
4.1 | Review and Confirm all onsite vendor activities
4.1.1 | Press Kit Delivered
4.1.2 | Signage Delivered and Installed
4.1.3 | Electrical, Cleaning and Internet Confirmed
4.1.4 | Giveaways and Other Materials Delivery Confirmed
4.2 | Booth Setup
4.3 | Meet and Brief with Company Attendees
5 | Onsite Exhibit Activities
5.1 | Monitor Lead Tracking
5.2 | Reserve Space for Next Year
6 | Post-Show Events
6.1 | Coordinate Return Shipping of Materials
6.2 | Oversee Booth Dismantlement
6.3 | Assess Event Success Based on Success Criteria
6.4 | Conduct De-Briefing for Lessons Learned
6.5 | Draft Event Report for Management Review
6.6 | Pass on Leads to Marketing