## Sheet1
Binfire Project Plan Template for Startups Funding Project
Task No | Task | Scheduled Start Date | Scheduled End Date | Dependencies | Estimated Effort (Days) | Business | Marketing | Finance | Product | Technology | Other | Comments
1 | Define Product/Service Concept
1.1 | Identify key features, unique value etc.
1.2 | Conduct high level market and competitive analysis
1.3 | Create a realistic visual mockup or visualization of one or more unique feature
1.4 | Verify concept by sharing mockup with initial group (potential target customers if possible)
1.5 | Modify concept and change mockup based on feedback
2 | Create Initial Team and Ownership Structure
2.1 | Identify founders
2.2 | Determine ownership percentages based on commitments (time and resources)
2.3 | Document all decisions to avoid future conflict
3 | Define Business Model
3.1 | Create multiple scenarios for commercialization of concept
3.2 | Define potential revenue model
3.3 | Test revenue concept by asking for feedback from potential customers
3.4 | Estimate future costs for each stage of company and product development
3.5 | Estimate timeline for breakeven point for each commercialization concept
3.6 | Define funding and business milestones based on selected commercialization concept
4 | Create Initial Resource Plan
4.1 | Identify location, equipment and other resource requirements
4.2 | Identify professional services needed (accounting, legal etc.)
4.3 | Explore alternatives to capital expenditures
4.4 | Determine cost for each resource
5 | Create a high level funding plan
5.1 | Map out each stage of growth
5.2 | Determine milestone for each stage of growth (functional prototype, initial X customers, etc.)
5.3 | Map out funding plan for each milestone
6 | Initial Seed Funding
6.1 | Define first funding milestone and estimate expenses until milestone achieved
6.2 | Explore Line of Credit options based on personal commitments
6.3 | Research Government funding and other public sector funding opportunities
6.4 | Research incubators and other corporate funding opportunities
6.5 | Identify friends and family that can provide initial funding
6.6 | Create financial terms (debt or equity) for initial funding
6.7 | Document financial terms
7 | Investor Funding Outreach
7.1 | Prepare list of documents including business plan and financial projections etc.
7.2 | Identify potential investors based on their previous funding records
7.3 | Create a short list to pitch
7.4 | Develop pitch deck
7.5 | Customize pitch based on investor outlook